## Track Table
Block | Priority (P0 > P3) | Propietario | Status | Start Date | Estimated End date | Logro | Producto final | Schematic status | Layout Status | PEX Status | Notes
Tutorials and Learning tools | P0 |  | In progress | 2025-06-30 | 2025-08-02 |  |  | Completed!!! | Place & Route in Process | Not Started
MOSBius Interface | P0 |  | In progress | 2025-07-15 | 2025-08-02 |  |  | TT in process | Not Started | Not Started
Ring Oscillator | P0 |  | In progress | 2025-07-28 | 2025-08-09 |  |  | PVT/MC in process | Place & Route in Process | Not Started
XOR Phase Detector | P1 |  | In progress | 2025-07-29 | 2025-08-11 |  |  | PVT/MC in process | Not Started | Not Started
Comparator | P0 |  | In progress | 2025-07-29 | 2025-08-23 |  |  | TT in process | Not Started | Not Started
Edge detector | P1 |  | In progress | 2025-08-05 | 2025-08-23 |  |  | PVT/MC in process | Not Started | Not Started
Integrator | P2 |  | In progress | 2025-07-31 | 2025-09-06 |  |  | PVT/MC in process | Not Started | Not Started
Low Pass Filter | P2 |  | In progress | 2025-09-10 | 2025-09-13 |  |  | PVT/MC in process | Not Started | Not Started
Neuron | P3 |  | In progress | 2025-09-10 | 2025-09-15 |  |  | TT in process | Not Started | Not Started
Chip Integration | P3 |  | Blocked | 2025-09-15 | 2025-09-26 |  |  | Not Started | Not Started | Not Started
FALSE
FALSE
FALSE
FALSE
FALSE